## Gantt
Task		Responsible Party	Due	Fri, 02/05/2010	Fri, 02/12/2010	Fri, 02/19/2010	Fri, 02/26/2010	Fri, 03/05/2010	Fri, 03/12/2010	Fri, 03/19/2010	Fri, 03/26/2010	Fri, 04/02/2010	Fri, 04/09/2010	Fri, 04/16/2010	Fri, 04/23/2010	Fri, 04/30/2010	Fri, 05/07/2010	Fri, 05/14/2010
Scrape Websites
	Create scrapers for each court that gather PDF files and convert to HTML (with alert on fail)	Longhao
	Dump PDFs and metadata as described by MoSCoW into MySQL database	Longhao
	Have scrapers functioning on slicehost each day at the proper time per court	Longhao

Make a Website
	Get Django Running Properly on Apache2/mod_wsgi/MySQL	Mike
	Add user accounts with options described by MoSCOW	Mike
	Create django back-end for configuring alerts and saving to profile	Mike
	Create django back end for RSS pages for court, primary author, party-name and panelist	Mike
	Create django back-end for case pages	Mike
	Create front-end for case pages (with hit highlighting)	Mike
	Design and create front-end for homepage	Mike
	Write privacy/licensing/contribute/contact pages	Mike
	Launch alpha site and send to testers	Mike
	Launch beta site and send to testers	Mike
	Final launch and thank you to testers	Mike

User Studies
	Interview various people	Mike
	Send first survey regarding boolean testing and blogs	Mike
	Contact users for testing (alpha)	Mike
	Contact users for testing (beta)	Mike
	Contact users for launch!	Mike

Filtering
	Complete analysis of FOSS search/filtering tools	Mike
	Spell check	Longhao
	Synonym list/support	Longhao
	Acronym list/support	Longhao
	Abbreviation list/support	Longhao
	Stop-word list/support	Longhao
	Stemming support	Longhao
	Hyphenation support	Longhao
	Facet by court jurisdiction	Longhao

Alert System
	Write alert text (HTML and plain text)	Mike
	Begin sending alerts	Longhao

Coursework
	Final paper outline	Longhao leads	?
	Final paper draft 1	Longhao leads	04/06/10
	Final paper final version	Longhao leads	05/06/10
	Final presentation draft 1	Mike leads	?
	Final presentation final version	Mike leads
	Final poster draft 1	Mike leads
	Final poster final version	Mike leads	05/07/10
	Mid Project approval form	Longhao, Mike	03/10/10
	Showcase	Longhao, Mike